# NeighborBridge Funding and Scaling Roadmap (3 Years)

(English & Chinese Version)

## Year 1 – Pilot & Proof (Foundation Phase)

Goal: Build credibility, measurable ROI, and stable revenue base.

| Focus | Key Actions | Funding / Partner Sources |
| --- | --- | --- |
| Clinical anchor | Continue FQHC work (2 days/week); add one PLLC/telehealth half-day for FASD/ADHD patients | FQHC salary + private billings |
| Education pilot | Launch NeighborBridge Education 3-tier family program with NCFASD Informed support | Family tuition (HSA/FSA) + small foundation mini-grants |
| Community integration | Recruit 2–3 CHWs through church/faith networks for 90-day pilot | Trillium / Alliance Tailored Plan reinvestment |
| Data & outcomes | Track 30 families; measure attendance, satisfaction, and follow-up adherence | Basis for future grants |

Outcome: 3 funded contracts + first $350k–$400k annualized revenue; evidence packet ready for Year 2 expansion.

## Year 2 – Regional Scaling (Growth Phase)

Goal: Replicate proven pilot across multiple counties; diversify funding.

| Focus | Key Actions | Funding / Partner Sources |
| --- | --- | --- |
| Tailored Plan integration | Sign 1–2 county contracts for CHW training & family navigation | Medicaid Tailored Plan community reinvestment funds |
| FQHC partnerships | Subcontract under HRSA Enabling Services or BHI supplement | $75k–$150k per site |
| NeighborBridge Education expansion | Offer CHW & school staff courses (non-PHI) | Tuition + local public-health funds |
| Institutional research tie-in | Partner Duke/Harvard/Yale for evaluation study | HRSA or NC DHHS grant collaboration |

Outcome: 4–6 active contracts; gross revenue ≈ $650k–$750k; formal evaluation data + press coverage.

## Year 3 – Network & Licensing (Scale Phase)

Goal: Establish statewide or multi-state youth behavioral-health education network.

| Focus | Key Actions | Funding / Partner Sources |
| --- | --- | --- |
| State-level contracts | Tailored Plans adopt NeighborBridge as reimbursable family-training vendor | DHHS / Medicaid innovation grants |
| Education IP licensing | License training dashboards & curriculum to FQHCs or county health | $5–10k / site annual license |
| CME & certification | Partner with university CME offices for 'FASD-Informed Care' | CME revenue + institutional fees |
| Philanthropic scaling | Secure multi-year Duke Endowment / Reynolds Trust funding | $250k–$500k / year |

Outcome: Statewide footprint; $1 million+ annual revenue; NeighborBridge recognized as NC model for FASD/ASD/IDD community education.

# NeighborBridge 三年资金与扩展路线图

（中英文版本）

## 第一年：试点与验证

目标：建立信任度与可测ROI，实现稳定收入基础。

| 重点方向 | 关键行动 | 资金 / 合作来源 |
| --- | --- | --- |
| 临床锚点 | 维持每周两天FQHC门诊，增加半天远程诊疗 | FQHC 薪资 + 私人账单 |
| 教育试点 | 启动NeighborBridge Education三层家长课程，与NCFASD Informed合作 | 家长学费（HSA/FSA）+ 小型基金会资助 |
| 社区整合 | 通过教会网络招募2–3名CHW进行90天试点 | Trillium / Alliance Tailored Plan再投资 |
| 数据与成果 | 追踪30个家庭的出勤率、满意度与依从性 | 后续申请更大项目依据 |

## 第二年：区域扩展

目标：在多个县复制成功试点，扩大资金来源。

| 重点方向 | 关键行动 | 资金 / 合作来源 |
| --- | --- | --- |
| Tailored Plan整合 | 签署1–2个县级CHW培训与家庭导航合同 | Medicaid再投资资金 |
| FQHC合作 | 作为HRSA社区外展或BHI补助的分包商 | $75k–$150k每站点 |
| 教育扩展 | 面向CHW与学校员工提供非PHI课程 | 学费 + 地方公共卫生经费 |
| 学术合作 | 与Duke/Harvard/Yale合作进行评估研究 | HRSA或NC DHHS资助 |

## 第三年：网络与授权

目标：建立全州或跨州青少年心理健康教育网络。

| 重点方向 | 关键行动 | 资金 / 合作来源 |
| --- | --- | --- |
| 州级合同 | 被Tailored Plans采纳为家庭教育可报销供应商 | DHHS / Medicaid创新基金 |
| 课程授权 | 向FQHC或县级卫生局授权教育课程与仪表盘 | $5–10k / 站点 / 年 |
| CME认证 | 与大学继续教育办公室合作推出‘FASD知情照护’课程 | CME收入 + 学术费用 |
| 基金会扩展 | 获得Duke Endowment或Reynolds Trust多年度资助 | $250k–$500k / 年 |